## Work order tracking form
Tracker Sheet PhotoManagerAI
Time | Assigned to | Work Assigned | % Complete | Status
1st Sep to 6th Sep | Logesh K | Research & Analysis | 100% | Complete
6th Sep to 15th Sep | Logesh K | Model selection and creation | 100% | Complete
20 Sep to 24 Sep | Logesh K | Model fine tuning and optimization | 60% | On Progress
20 Sep to 24 Sep | Navin E | Creation of Home page for webpage | 40% | On Progress
20 Sep to 24 Sep | Anas Henry A | Creation of Registeration page | 60% | On Progress
20 Sep to 24 Sep | Jeyachandran J | Handling backend processes | 0% | Not Yet Started